## Read Me
Shared Power Bank OEM Due Diligence Scorecard 2026
A two-stage procurement tool: preliminary score after documents, demos and samples; final score after pilot and support validation.
How to use this workbook
1 | Define the market and requirement | Target country, venue mix, rental path, payment route, launch date and intended scale.
2 | Clear critical pauses | Assess the six pause conditions before advancing. An open pause overrides the numeric score.
3 | Issue the preliminary score | Review documents, run normal/exception demos and approve samples. Pilot and support items remain provisional.
4 | Select pilot candidate(s) | Contract the golden sample, controlled baseline, payment, data, acceptance and support terms.
5 | Run the pilot and support test | For projects intended to scale, consider 50–100 stations across varied venues and placements; adjust to the project.
6 | Issue the final score | Release a scaled order only after acceptance, corrective actions and critical conditions are closed.
Decision thresholds |  |  |  | Color key
Score / condition | Preliminary decision | Final decision | Meaning | Color | Meaning | Action
80–100 | Eligible for pilot | Eligible for scaled rollout | Close remaining non-critical conditions | Yellow | Editable input | Complete or update
70–79 | Remediate before pilot | Remediate before scale | Document actions and re-verify | Green | Clear / pass | Retain evidence
Below 70 | Do not advance | Do not scale | Material gaps remain | Orange | Remediation | Assign owner and deadline
Any open critical pause | PAUSE | PAUSE | Numeric score cannot override a pause | Red | Pause / fail | Stop and resolve
Important limitations
• | This 100-point method is a Bajie Charging procurement framework, not a mandatory industry standard. Adjust weights and criteria to the project.
• | An integrated payment channel is not automatically available to every merchant in every country. Verify eligibility, onboarding, settlement and production behavior.
• | Data, app-account and intellectual-property rights depend on the contract. Obtain legal and compliance advice in the target market.
• | Suggested article URL: https://www.bajie-charging.com/blog/shared-power-bank-oem-supplier-due-diligence-checklist/

## Scorecard
OEM Supplier Scorecard — Preliminary and Final
Enter scores from 0 up to each row's weight. Yellow cells are inputs. Resolve critical pauses before any stage can advance.
Preliminary score |  | Preliminary decision |  | Final score |  | Final decision |  | Open pauses |  | Scored items
|  | INCOMPLETE |  |  |  | INCOMPLETE |  | 0 |  | 0/12 preliminary; 0/12 final
Scoring rule: full points only when evidence is complete and the relevant test passes; partial points for documented correctable gaps; zero when the claim cannot be verified.
Gate | Due-diligence item | Weight | Evaluation focus | Preliminary score | Final score | Evidence status | Key evidence / link | Gap / corrective action | Owner | Due date | Notes
Company & manufacturing | 1. Legal identity and supplier type | 5 | Contracting, payment, invoice, manufacturing, software and support responsibility chain |  |  | Not Requested
Company & manufacturing | 2. Factory, R&D and relevant experience | 7 | Live capability, relevant project evidence and accountable technical team |  |  | Not Requested
Company & manufacturing | 3. Production, QC and traceability | 8 | Incoming/in-process/outgoing control, serial trace, BOM and change control |  |  | Not Requested
Hardware & compliance | 4. Product-specific compliance and transport | 12 | Exact configuration, market documents, UN 38.3 test summary and shipping readiness |  |  | Not Requested
Hardware & compliance | 5. Reliability, materials and serviceability | 13 | Lifecycle tests, critical parts, repair path and operating limits |  |  | Not Requested
Software, payment & data | 6. Hardware–software–IoT integration | 8 | Normal and exception events, state consistency, monitoring and recovery |  |  | Not Requested
Software, payment & data | 7. App, dashboard, accounts and APIs | 7 | Roles, exports, API/webhook proof, app/account control |  |  | Not Requested
Software, payment & data | 8. Local payment lifecycle | 10 | Eligibility, success/failure, pre-auth, refund, settlement and reconciliation |  |  | Not Requested
Software, payment & data | 9. Data, IP, security and exit rights | 10 | Contracted ownership/license, access, export, security, deletion and migration |  |  | Not Requested
Delivery, pilot & support | 10. Sample, production consistency and pilot | 7 | Golden sample, locked baseline, production inspection and representative pilot |  |  | Not Requested
Delivery, pilot & support | 11. Customization, change, delivery and logistics | 5 | Scope, approvals, change orders, milestones, Incoterm and shipping documents |  |  | Not Requested
Delivery, pilot & support | 12. Warranty, RMA, spares, SLA and TCO | 8 | Coverage, exclusions, freight, response, escalation, spare plan and three-year cost |  |  | Not Requested
TOTAL |  | 100 |  | 0 | 0

## Critical Pauses
Critical Pause Conditions
An open pause overrides the numeric score. Mark every condition Clear, Open, Resolved or Not Applicable before a stage decision is complete.
Overall status | INCOMPLETE | Not assessed | 6 | Open | 0 | Resolved | 0
ID | Critical condition | Status | Stage | Evidence / link | Corrective action | Owner | Due date | Notes
P1 | Contracting, receiving, invoicing and manufacturing entities cannot be reconciled. | Not Assessed | Both
P2 | Required compliance or transport documents do not match the exact product, radio and battery configuration. | Not Assessed | Both
P3 | The target-market payment lifecycle cannot be verified, and no credible integration plan exists. | Not Assessed | Both
P4 | The supplier refuses to define data export, service termination and migration rights in the contract. | Not Assessed | Both
P5 | The golden sample, critical BOM or firmware baseline cannot be locked, or changes may occur without notice. | Not Assessed | Both
P6 | Acceptance, warranty, RMA or serious-incident escalation responsibilities remain undefined. | Not Assessed | Both

## Evidence Tracker
Evidence Document Tracker
Track what was requested, what configuration it covers, who reviewed it and which gaps must be closed.
Verified | 0 | Requested / received | 0 | Rejected | 0 | Total items | 24
Item | Gate | Evidence requested | Required? | Stage | Status | File / URL | Product / configuration | Issue / expiry | Reviewer | Finding | Corrective action | Owner / due date
1 | Company & manufacturing | Business registration, contract entity and matching bank beneficiary | Yes | Preliminary | Not Requested
1 | Company & manufacturing | Responsibility chart and critical subcontractor disclosure | Yes | Preliminary | Not Requested
2 | Company & manufacturing | Live factory audit covering production and nonconforming material | Yes | Preliminary | Not Requested
2 | Company & manufacturing | R&D structure and relevant anonymized project evidence | Yes | Preliminary | Not Requested
3 | Company & manufacturing | Quality plan and incoming/in-process/outgoing inspection records | Yes | Preliminary | Not Requested
3 | Company & manufacturing | Serial/batch trace, critical BOM and change-control example | Yes | Both | Not Requested
4 | Hardware & compliance | Target-market compliance matrix for exact configuration | Yes | Preliminary | Not Requested
4 | Hardware & compliance | Declarations, test reports and responsible-party records | Yes | Preliminary | Not Requested
4 | Hardware & compliance | UN 38.3 test summary, SDS and transport document set | Yes | Preliminary | Not Requested
5 | Hardware & compliance | Product specification, critical component and operating-limit list | Yes | Preliminary | Not Requested
5 | Hardware & compliance | Lifecycle/reliability tests, service manual and spare list | Yes | Both | Not Requested
6 | Software, payment & data | Architecture, event flow and representative device logs | Yes | Preliminary | Not Requested
6 | Software, payment & data | Exception test: power/network interruption and state recovery | Yes | Both | Not Requested
7 | Software, payment & data | Role-based app/dashboard demo and functional specification | Yes | Preliminary | Not Requested
7 | Software, payment & data | API/webhook documentation, sandbox access and export samples | As needed | Preliminary | Not Requested
8 | Software, payment & data | Country payment feasibility and merchant onboarding requirements | Yes | Preliminary | Not Requested
8 | Software, payment & data | Payment lifecycle, funds flow, settlement and reconciliation evidence | Yes | Both | Not Requested
9 | Software, payment & data | Asset/account/IP rights matrix and data-processing terms | Yes | Preliminary | Not Requested
9 | Software, payment & data | Security summary, subprocessors, export and exit test | Yes | Both | Not Requested
10 | Delivery, pilot & support | Signed requirements, golden sample and controlled baseline | Yes | Preliminary | Not Requested
10 | Delivery, pilot & support | Production inspection, pilot report and corrective-action closure | Yes | Final | Not Requested
11 | Delivery, pilot & support | Customization scope, approvals, change-order and milestone plan | Yes | Preliminary | Not Requested
11 | Delivery, pilot & support | Incoterm, packing, logistics and customs document checklist | Yes | Preliminary | Not Requested
12 | Delivery, pilot & support | Warranty, RMA, spares, SLA, escalation and support-test record | Yes | Both | Not Requested

## Pilot Acceptance
Pilot and Business Acceptance
Suggested scale for projects intended to roll out: consider 50–100 stations across multiple venue types and exact in-venue placements. This is not a universal minimum.
Passed | 0 | Failed / blocked | 0 | Not started | 12 | Total tests | 12
Test ID | Area | KPI / acceptance test | Target / criterion | Measurement method | Pilot scope / venue / placement | Actual result | Status | Evidence / link | Corrective action | Owner | Retest date
T01 | Availability | Station online and charged-unit availability | Set from service plan | Daily uptime and available-unit records |  |  | Not Started
T02 | Rental | Successful dispense and order creation | Set before pilot | Compare command, physical dispense and order log |  |  | Not Started
T03 | Return | Correct slot recognition and billing stop | Set before pilot | Compare return event, device state and invoice |  |  | Not Started
T04 | Payment | Successful local payment | Production path passes | Gateway, order and station record match |  |  | Not Started
T05 | Payment | Decline, timeout, duplicate callback and retry | No unintended dispense/duplicate charge | Scripted exception cases |  |  | Not Started
T06 | Payment | Refund, partial refund, pre-auth/deposit release | Matches contract and gateway | Gateway and finance reconciliation |  |  | Not Started
T07 | Recovery | Power/network interruption and recovery | No unresolved state mismatch | Controlled interruption and log review |  |  | Not Started
T08 | Remote operations | Alert, diagnosis, OTA/reset or remote action | Defined action succeeds | Operator and audit-log review |  |  | Not Started
T09 | Support | Real support ticket from acknowledgment to closure | Meets contracted SLA | Ticket timestamps and resolution evidence |  |  | Not Started
T10 | Location | Venue type and exact placement comparison | Decision threshold from business plan | Rentals and availability by site/position |  |  | Not Started
T11 | Operations | Field labor, visits, spares and repair burden | Within operating plan | Time sheet, parts and visit log |  |  | Not Started
T12 | Finance / TCO | Orders, gateway and finance reconcile; pilot TCO updated | No unexplained variance | Reconciliation and TCO workbook |  |  | Not Started

## 3-Year TCO
Three-Year Total Cost of Ownership Comparison
Enter initial Year 0 costs plus operating Years 1–3. Use one currency consistently and include downtime and exit costs—not only hardware price.
Currency | USD |  | Supplier A | Supplier B | Supplier C
3-year TCO |  |  | 0 | 0 | 0
Decision note: compare three-year cost together with the final due-diligence score, unresolved risks and operating fit.
Category | Cost item | Year | Supplier A | Supplier B | Supplier C | Notes / source
Initial system | Stations / cabinets | 0
Initial system | Stations / cabinets | 1
Initial system | Stations / cabinets | 2
Initial system | Stations / cabinets | 3
Initial system | Rental power banks | 0
Initial system | Rental power banks | 1
Initial system | Rental power banks | 2
Initial system | Rental power banks | 3
Initial system | Branding, tooling and packaging setup | 0
Initial system | Branding, tooling and packaging setup | 1
Initial system | Branding, tooling and packaging setup | 2
Initial system | Branding, tooling and packaging setup | 3
Initial system | Samples and pilot setup | 0
Initial system | Samples and pilot setup | 1
Initial system | Samples and pilot setup | 2
Initial system | Samples and pilot setup | 3
Software | Setup and customization | 0
Software | Setup and customization | 1
Software | Setup and customization | 2
Software | Setup and customization | 3
Software | License, cloud and maintenance | 0
Software | License, cloud and maintenance | 1
Software | License, cloud and maintenance | 2
Software | License, cloud and maintenance | 3
Software | Version upgrades and support | 0
Software | Version upgrades and support | 1
Software | Version upgrades and support | 2
Software | Version upgrades and support | 3
Payments | New gateway / acquirer integration | 0
Payments | New gateway / acquirer integration | 1
Payments | New gateway / acquirer integration | 2
Payments | New gateway / acquirer integration | 3
Payments | Transaction, refund and chargeback costs | 0
Payments | Transaction, refund and chargeback costs | 1
Payments | Transaction, refund and chargeback costs | 2
Payments | Transaction, refund and chargeback costs | 3
Third-party services | SIM/data, SMS, maps, email, domains and app accounts | 0
Third-party services | SIM/data, SMS, maps, email, domains and app accounts | 1
Third-party services | SIM/data, SMS, maps, email, domains and app accounts | 2
Third-party services | SIM/data, SMS, maps, email, domains and app accounts | 3
Compliance & logistics | Testing, documentation and certification updates | 0
Compliance & logistics | Testing, documentation and certification updates | 1
Compliance & logistics | Testing, documentation and certification updates | 2
Compliance & logistics | Testing, documentation and certification updates | 3
Compliance & logistics | Dangerous-goods freight, customs and destination charges | 0
Compliance & logistics | Dangerous-goods freight, customs and destination charges | 1
Compliance & logistics | Dangerous-goods freight, customs and destination charges | 2
Compliance & logistics | Dangerous-goods freight, customs and destination charges | 3
Operations | Deployment, site visits, redistribution and training | 0
Operations | Deployment, site visits, redistribution and training | 1
Operations | Deployment, site visits, redistribution and training | 2
Operations | Deployment, site visits, redistribution and training | 3
Maintenance | Spare parts, repairs and RMA freight | 0
Maintenance | Spare parts, repairs and RMA freight | 1
Maintenance | Spare parts, repairs and RMA freight | 2
Maintenance | Spare parts, repairs and RMA freight | 3
Maintenance | Battery, cable and other wear-item replacement | 0
Maintenance | Battery, cable and other wear-item replacement | 1
Maintenance | Battery, cable and other wear-item replacement | 2
Maintenance | Battery, cable and other wear-item replacement | 3
Downtime | Lost rental contribution and emergency replacement | 0
Downtime | Lost rental contribution and emergency replacement | 1
Downtime | Lost rental contribution and emergency replacement | 2
Downtime | Lost rental contribution and emergency replacement | 3
Change | Custom features, APIs and new payment work | 0
Change | Custom features, APIs and new payment work | 1
Change | Custom features, APIs and new payment work | 2
Change | Custom features, APIs and new payment work | 3
Exit | Data export, migration and account transfer | 0
Exit | Data export, migration and account transfer | 1
Exit | Data export, migration and account transfer | 2
Exit | Data export, migration and account transfer | 3
Other | Other project-specific cost | 0
Other | Other project-specific cost | 1
Other | Other project-specific cost | 2
Other | Other project-specific cost | 3