FIELD WORKBOOK  ·  2026

Shared Power Bank 90-Day Pilot Validation Scorecard

A printable, evidence-led workbook for a 30 / 60 / 90-day pilot review.

RED LINE  →  EVIDENCE  →  WEIGHTED REVIEW  →  HUMAN DECISION
  →    →    →

Bajie Charging  |  Bilingual Edition

Version 1.0  ·  Project-specific targets required before interpretation

| Control item | Record |
| --- | --- |
| Version | 1.0 |
| Review cycle | Day 30 · Day 60 · Day 90 |
| Project name |  |
| Document owner |  |

1. Usage rules and limitations

The 50–100-station range is Bajie Charging's planning reference for scale-intended validation, not a universal minimum, purchase requirement or success threshold.

Ninety days is a planning and review cycle, not a profitability, ROI or payback promise; a project may approve a different observation period and should explain any extension.

Targets and interpretation bands are project-specific, must be approved before use and cannot override an open red-line blocker; this scorecard defines no public fixed Go cut-off.

Payment availability depends on country, merchant entity, currency, provider approval and project scope.

Averages do not replace analysis of distribution, venue role, exceptions and change history; missing evidence must be disclosed rather than estimated or invented.

Calculated completion and weighted scores support review but never automatically declare market success or readiness to scale; management records the final human decision.

2. Pilot Charter and approval block

Complete and approve this block before pilot interpretation.

| Charter field | Shared project answer area |
| --- | --- |
| Business question |  |
| Scope, station range and approved exposure |  |
| Decision owner and review calendar |  |
| Interpretation bands and change control |  |
| Approval signatures and dates |  |

3. Market-readiness and red-line gate

Only a red line explicitly assessed as closed is cleared; a not assessed or open red line makes Go unavailable.

| Red-line blocker | Status | Impact | Containment | Owner · due date | Closure evidence Retest result Approver |
| --- | --- | --- | --- | --- | --- |
| Uncontrolled safety or regulatory risk | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |
| Production payment, collection or settlement responsibility is unclear | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |
| Incorrect billing, payment-without-release or refund failure lacks an effective control | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |
| Reconciliation cannot connect orders, payments, releases, returns and refunds | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |
| Privacy, access control or sensitive-data exposure is uncontrolled | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |
| Required venue permission or operating authorization is missing | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |
| Critical source data is unavailable, materially incomplete or not auditable | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |
| A critical device, software or payment failure repeats after corrective action | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |
| A material incident has no accountable owner or escalation route | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |
| The pilot exceeds its approved budget, station scope or risk exposure without authorization | ☐ Not assessed ☐ Open ☐ Closed |  |  |  |  |

4. Deployment register

| Station | Venue and role | Go-live date | Owner | Exceptions |
| --- | --- | --- | --- | --- |

5. Go-live acceptance checklist

| Acceptance item | Evidence and result | Owner | Status |
| --- | --- | --- | --- |
| Venue authorization and physical safety |  |  | ☐ Pass ☐ Conditional ☐ Blocked |
| Payment, release and refund controls |  |  | ☐ Pass ☐ Conditional ☐ Blocked |
| Connectivity, fleet state and monitoring |  |  | ☐ Pass ☐ Conditional ☐ Blocked |
| Data access, privacy and reconciliation |  |  | ☐ Pass ☐ Conditional ☐ Blocked |
| Support, incident and escalation route |  |  | ☐ Pass ☐ Conditional ☐ Blocked |

6. KPI dictionary and evidence-definition sheet

| KPI | Definition and formula | Source, rules and time basis | Owner |
| --- | --- | --- | --- |

7. Seven-dimension weighted scorecard

Dimension score = average criterion score ÷ 4 × dimension weight. Total score = sum of the seven dimension scores (maximum 100).

User Demand & Activation

| Criterion | Shared evidence and answer area | Score (0–4) |
| --- | --- | --- |
| Observed user need | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Station discovery and journey clarity | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Demand-to-rental funnel | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Demand evidence coverage | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |

User & Payment Journey
Weight  : 20 points

| Criterion | Shared evidence and answer area | Score (0–4) |
| --- | --- | --- |
| Pricing, terms and support disclosure | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Live payment completion | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Payment, order and release integrity | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Return and billing completion | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Refund, dispute and reconciliation control | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |

System & Fleet Availability 
Weight: 15 points

| Criterion | Shared evidence and answer area | Score (0–4) |
| --- | --- | --- |
| Station online and service availability | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Rentable inventory and fleet balance | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Return-state and inventory integrity | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Fault diagnosis and recovery | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |

Venue & Network Effectiveness 
Weight: 15 points

| Criterion | Shared evidence and answer area | Score (0–4) |
| --- | --- | --- |
| Representative venue mix | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| In-venue position effectiveness | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Defined network roles | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Network distribution and return usefulness | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |

Operations & Support Repeatability 
Weight : 15 points

| Criterion | Shared evidence and answer area | Score (0–4) |
| --- | --- | --- |
| Routine operating control | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Incident and support closure | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Measured operating workload | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Operating process repeatability | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |

Merchant Development & Cooperation  
Weight  : 10 points

| Criterion | Shared evidence and answer area | Score (0–4) |
| --- | --- | --- |
| Venue development funnel | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Merchant onboarding readiness | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Merchant cooperation and retention | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |

Data & Economic Traceability 
Weight : 10 points

| Criterion | Shared evidence and answer area | Score (0–4) |
| --- | --- | --- |
| Approved KPI dictionary | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Source quality and auditability | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Traceable operating costs | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |
| Material change history | Definition ________________________________________________________________ Project-specific target ________________________________________________________________ Source · period · coverage ________________________________________________________________ Day-30 / 60 / 90 result ________________________________________________________________ Exception · evidence reference · confidence ________________________________________________________________ Conclusion status · owner · due date · retest ________________________________________________________________ | ☐ 0 ☐ 1 ☐ 2 ☐ 3 ☐ 4 ________________________________________________________________ Score ________________________________________________________________ |

| Dimension | Weight | Dimension score (blank) |
| --- | --- | --- |
| User Demand & Activation | 15 |  |
| User & Payment Journey | 20 |  |
| System & Fleet Availability | 15 |  |
| Venue & Network Effectiveness | 15 |  |
| Operations & Support Repeatability | 15 |  |
| Merchant Development & Cooperation | 10 |  |
| Data & Economic Traceability | 10 |  |
| Total score | 100 |  |

8. Day-30 stability review: Stabilize/Restrict/Proceed

| Review prompt | Shared answer area |
| --- | --- |
| Stability evidence and critical exceptions |  |
| ☐ Stabilize ☐ Restrict ☐ Proceed — rationale |  |
| Condition, owner and due date |  |

9. Day-60 adjustment review and final-phase hypotheses

| Hypothesis or adjustment | Variable and affected stations | Owner · due date · retest window |
| --- | --- | --- |

10. Issue, corrective-action and retest register

| Issue | Corrective action | Owner · due date | Retest result | Status |
| --- | --- | --- | --- | --- |

11. Day-90 Evidence Pack completeness index

| Evidence item | Reference and coverage | Completeness | Reviewer |
| --- | --- | --- | --- |
| Approved charter and change history |  | ☐ Complete ☐ Partial ☐ Missing |  |
| Deployment and go-live acceptance |  | ☐ Complete ☐ Partial ☐ Missing |  |
| KPI extracts and reconciliation |  | ☐ Complete ☐ Partial ☐ Missing |  |
| Incident, corrective-action and retest records |  | ☐ Complete ☐ Partial ☐ Missing |  |
| Venue, payment, privacy and authorization evidence |  | ☐ Complete ☐ Partial ☐ Missing |  |

12. Go / Adjust / Stop decision sheet and controlled-scale conditions

Select and approve a management decision only after review. This workbook does not make the decision automatically.

| Human decision | Definition | Conditions, approver and date |
| --- | --- | --- |
| ☐ Go | All red lines are closed; reliable evidence supports controlled replication; the team can support a defined next wave; remaining risks have owners and limits. |  |
| ☐ Adjust | The opportunity remains plausible but repairable gaps or insufficient evidence remain; the next test states the variable, owner, due date, affected stations and retest window; no uncontrolled expansion occurs before review. |  |
| ☐ Stop | A critical risk remains open, a material issue repeats after correction, evidence cannot be audited, or the proposed operating model cannot be supported; the exit plan covers users/orders/refunds, assets, venues, data and suppliers. |  |

13. Exit-plan checklist for Stop decisions

| Exit item | Owner and due date | Evidence of completion |
| --- | --- | --- |
| Users, open orders and refunds |  |  |
| Assets, station removal and inventory |  |  |
| Venues, suppliers and communications |  |  |
| Data export, retention and access closure |  |  |